## Sheet1
Fast Food Management: Campus Munchies
Back log Group 5 | [7 empty] | EASY | MEDIUM | COMPLEX
Function Name | Feature | Complexity | Deadline | Roll Number | Name | Time: Finish | Note
Customer
Log in/ Logout | Log in | EASY | Oct 20th | CE170135 | Duong Si Tien | Oct 15th
| Log out | EASY | Oct 20th | CE170284 | Ta Minh Khang | Oct 15th
| Forget Password | COMPLEX | Nov 1st | CE171382 | Tran Tien | Nov 1st
Menu | Show all the menu | EASY | Oct 20th | CE170135 | Duong Si Tien | Oct 17th
| Search By Name (Live Search) | COMPLEX | Oct 20th | CE170284 | Ta Minh Khang | Oct 17th
| Search By Category (Live Search) | COMPLEX | Oct 30th | CE170285 | Ta Minh Khang | Oct 29th
| View Details | EASY | Oct 20th | CE170135 | Ta Minh Khang | Oct 17th
Cart | Show food from cart | EASY | Oct 20th | CE170135 | Duong Si Tien | Oct 15th
| Add food to cart | EASY | Oct 20th | CE170284 | Ta Minh Khang | Oct 15th
| Delete from cart | EASY | Oct 20th | CE170284 | Ta Minh Khang | Oct 18th
| Add quantity | EASY | Oct 20th | CE170284 | Ta Minh Khang | Oct 18th
| Add check box for each food | EASY | Oct 20th | CE170284 | Ta Minh Khang | Oct 18th
Order food | Show detail of order | MEDIUM | Oct 22th | CE170284 | Ta Minh Khang | Oct 18th
| Purchase | MEDIUM | Oct 22th | CE170284 | Ta Minh Khang | Oct 18th
Profile | Change information | EASY | Oct 22th | CE170135 | Duong Si Tien | Oct 22th
| Change password | EASY | Oct 22th | CE170135 | Duong Si Tien | Oct 22th
Order History | Show Order History | EASY | Oct 25th | CE170284 | Ta Minh Khang | Oct 22th
| Show Order detail | MEDIUM | Oct 30th | CE170134 | Duong Si Tien | Oct 29th
| Cancel Order | MEDIUM | Oct 30th | CE170284 | Ta Minh Khang | Oct 29th
Guest
Register | Register | MEDIUM | Oct 20th | CE170135 | Duong Si Tien | Oct 15th
Menu | Show all the menu | EASY | Oct 20th | CE170135 | Duong Si Tien | Oct 17th
| Search By Name (Live Search) | COMPLEX | Oct 20th | CE170284 | Ta Minh Khang | Oct 17th
| Search By Category (Live Search) | COMPLEX | Oct 20th | CE170284 | Ta Minh Khang | Oct 17th
| View Details | EASY | Oct 20th | CE170135 | Duong Si Tien | Oct 17th
Employee
Login of employee | Login | MEDIUM | Oct 22th | CE170883 | Do Dang Khoa | Oct 15th
Order List | Show Order List of an employee | MEDIUM | Oct 22th | CE170883 | Do Dang Khoa | Oct 15th
| Search Order by Order Id | MEDIUM | Oct 22th | CE170883 | Do Dang Khoa | Oct 19th
| Search Order by date | MEDIUM | Oct 22th | CE170883 | Do Dang Khoa | Oct 19th
Order Detail | Update status order | MEDIUM | Oct 22th | CE170883 | Do Dang Khoa | Oct 19th
Customer Information | View | MEDIUM | Oct 22th | CE170883 | Do Dang Khoa | Oct 19th
Logout | Logout | EASY | Oct 22th | CE170883 | Do Dang Khoa | Oct 19th
Update profile | Update profile of employee | MEDIUM | Oct 23th | CE170883 | Do Dang Khoa | Oct 22th
New Order List | View | EASY | Oct 24th | CE170883 | Do Dang Khoa | Oct 23th
| Take new order | EASY | Oct 24th | CE170883 | Do Dang Khoa | Oct 23th
Change password | Change password | MEDIUM | Oct 25th | CE170883 | Do Dang Khoa | Oct 23th
Forgot password | Forgot password | MEDIUM | Oct 25th | CE170883 | Do Dang Khoa | Oct 23th
Manager
Login for Manager | Login | EASY | Oct 22th | CE171382 | Tran Tien | Oct 21th
Analytics | Show information: total revenue, total customer, total order | MEDIUM | Oct 22th | CE171382 | Tran Tien | Oct 21th
| Show list new user | MEDIUM | Oct 22th | CE171382 | Tran Tien | Oct 21th
| Show list recent order | MEDIUM | Oct 22th | CE171382 | Tran Tien | Oct 21th
Employee Management | Show list all employee | MEDIUM | Oct 22th | CE170789 | Tran Truong Vu | Oct 21th
| Search by name, phone, id for employee | MEDIUM | Oct 22th | CE170789 | Tran Truong Vu | Oct 21th
| Sort list employee | MEDIUM | Oct 22th | CE170789 | Tran Truong Vu | Oct 21th
| Create account for employee | COMPLEX | Oct 22th | CE171492 | Nguyen Nguyen Khanh | Oct 21th
| Delete account employee | MEDIUM | Oct 22th | CE170789 | Tran Truong Vu | Oct 21th
| Show list honor employee | MEDIUM | Oct 22th | CE170789 | Tran Truong Vu | Oct 21th
Employee Information Detail | Show employee information detail | MEDIUM | Oct 22th | CE171382 | Tran Tien | Oct 21th
| Show order served of employee | MEDIUM | Oct 22th | CE171382 | Tran Tien | Oct 21th
Customer Management | Show list all customer | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
| Search by name, phone, id for customer | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
| Sort list customer | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
| Show list of customers who cancel orders with the most orders | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
| Delete account customer | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
| Block account customer | COMPLEX | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
| Show list honor customer | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
Customer Information Detail | Show customer information detail | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
| Show history order of customer | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
Order Management | Show list all order | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
| Search by phone, id for order | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
| Sort list order | MEDIUM | Oct 25th | CE171492 | Nguyen Nguyen Khanh | Oct 24th
Order Information Detail | Show order information detail | MEDIUM | Oct 30th | CE171492 | Nguyen Nguyen Khanh | Oct 30th
| Show invoice information | MEDIUM | Oct 30th | CE171492 | Nguyen Nguyen Khanh | Oct 30th
Menu Management | Show list all food | MEDIUM | Oct 30th | CE171492 | Nguyen Nguyen Khanh | Oct 30th
| Search by name | MEDIUM | Oct 30th | CE171492 | Nguyen Nguyen Khanh | Oct 30th
| Filter category | MEDIUM | Oct 30th | CE171492 | Nguyen Nguyen Khanh | Oct 30th
| Update food | COMPLEX | Oct 30th | CE171492, CE170789 | Nguyen Nguyen Khanh, Tran Truong Vu | Oct 30th
| Add food | COMPLEX | Oct 30th | CE171492, CE170789 | Nguyen Nguyen Khanh, Tran Truong Vu | Oct 30th
| Delete food | MEDIUM | Oct 30th | CE171492 | Nguyen Nguyen Khanh | Oct 30th
Front-end
Log in form guest |  | MEDIUM | Oct 16th | CE170135, CE170789 | Duong Si Tien, Tran Truong Vu | Oct 15th
Register form guest |  | MEDIUM | Oct 16th | CE170135, CE170789 | Duong Si Tien, Tran Truong Vu | Oct 15th
Customer history |  | EASY | Oct 22th | CE170135 | Duong Si Tien | Oct 18th
Customer history detail |  | EASY | Oct 22th | CE170135 | Duong Si Tien | Oct 18th
Customer Cart |  | EASY | Oct 22th | CE170135 | Duong Si Tien | Oct 18th
Customer and guest home |  | MEDIUM | Oct 22th | CE170284 | Ta Minh Khang | Oct 15th
Customer and guest menu |  | COMPLEX | Oct 20th | CE170284 | Ta Minh Khang | Oct 17th
Customer and guest food details |  | MEDIUM | Oct 20th | CE170789 | Tran Truong Vu | Oct 17th
About Us |  | EASY | Oct 21th | CE170789 | Tran Truong Vu | Oct 19th
Forget Password form (customer) |  | EASY | Oct 21th | CE171382 | Tran Tien | Oct 19th
Profile Form (Customer) |  | MEDIUM | Oct 21th | CE171382 | Tran Tien | Oct 19th
Login form(Employee) |  | EASY | Oct 20th | CE170883 | Do Dang Khoa | Oct 15th
Order List(Employee) |  | EASY | Oct 20th | CE170883 | Do Dang Khoa | Oct 15th
Order Detail |  | EASY | Oct 20th | CE170883 | Do Dang Khoa | Oct 19th
Customer Infomation |  | EASY | Oct 20th | CE170883 | Do Dang Khoa | Oct 19th
Profile Employee |  | EASY | Oct 24th | CE170883 | Do Dang Khoa | Oct 23th
New Order List |  | EASY | Oct 24th | CE170883 | Do Dang Khoa | Oct 23th
Change Password |  | EASY | Oct 25th | CE170883 | Do Dang Khoa | Oct 23th
Forgot Password |  | EASY | Oct 25th | CE170883 | Do Dang Khoa | Oct 23th
Login(Manager) |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Analytics |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Emloyee Management |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Employee Details |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Customer Management |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Customer Details |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Order Management |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Order Details |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Menu |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Update Food |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Add Food |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Add Account |  | EASY | Oct 18th | CE171492 | Nguyen Nguyen Khanh | Oct 15th
Image, Logo, Banner |  | MEDIUM | Oct 30th | CE171382,CE170789 | Tran Tien, Tran Truong Vu | Oct 29th
Database
Database |  |  | Oct 16th | CE170135 | Duong Si Tien | Oct 11th
|  |  |  | CE170789 | Tran Truong Vu | Oct 11th
Document
Software Requirement Specification |  |  | Nov 5th | CE171382,CE170135 | Tran Tien, Duong Si Tien | Nov 5th
Software Design Document
Web App Guide Document
Report
Roll number | Name | Task* (%)
CE170284 | Ta Minh Khang | 14.95
CE171492 | Nguyen Nguyen Khanh | 29.91
CE170883 | Do Dang Khoa | 18.69
CE171382 | Tran Tien | 10.28
CE170135 | Duong Si Tien | 15.89
CE170789 | Tran Truong Vu | 10.28
Total |  | 100
*The percentage of work is based on the number of tasks of each member compared to the total number of tasks